[image: image1.png]Deloitte






Project Manager 

Description

The project manager has the authority to run the project on a day-to-day basis on behalf of the project board, within established constraints. The role of the project manager is to verify that the project produces the required deliverables at the required standard of quality, within the specified constraints of time and cost, and to achieve the potential benefits defined in the business case.

The assignment of a Deloitte project manager does not eliminate the need for the client to assign a full time project manager who must always retain ownership of the project and direct the project activities. The Deloitte project manager assists the client project manager as needed, but does not assume ownership of or overall responsibility for the project.

The project manager may delegate or assign responsibilities to the team lead, project controller, or project member for specific areas such as risk, quality, communication, or product deliverables. The project manager should clearly document which responsibility is being delegated and the level of assignment for the responsibility. The level of assignment may include participation, accountability, review, input, or sign-off. Roles and Responsibilities (part of Organizational Plan) can be used to map the subject areas being assigned to the roles. 

Two individuals normally serve the project manager role: one from the organization and one from Deloitte. These individuals concur and share the responsibilities.

A program manager performs many of the responsibilities of the project manager, but over several projects and functional units. A program manager may also replace the project director on any specific project or be assigned specific responsibilities. A program manager may delegate certain responsibilities to team leads, project controllers, and project members. 

Abbreviation 

ProjMgr

Responsibilities 

Communications Management

· Assist in identifying key stakeholders. 

· Assist in ranking key stakeholder groups. 

· Collect and monitor feedback on the effectiveness of project communications; update and coordinate the Internal Project Communications Plan; and coordinate the activities of various communicators, team leads, and project members.

· Develop and coordinate program-level communication. 

· Develop and deliver “key messages” throughout the implementation. 

· Develop communications strategy and Internal Project Communications Plan.

· Develop new ways to communicate project processes. 

· Draft and present appropriate key messages to stakeholders. 

· Encourage open, two-way communications. 

· Establish document management procedures, maintain a central project file, and maintain a Deloitte project file.

· Manage program- and project-level tracking and reporting. 

· Perform internal communications planning for the project, including determining the information and communications needs of the stakeholders, when they will need it, and how it will be provided to them.

· Prepare the closing project report. 

· Prepare the lessons learned report. 

· Provide feedback to team leaders.

· Provide status updates of communications activities and provide feedback received to the project director and others as requested.

· Report on project progress as requested or scheduled. 

· Report to the project board and project director through performance reports and phase assessments. 

· Conduct project communication and status reporting between teams and management. 

· Verify that the project director, team leads, and project members have the information they need to support effective communications. 

Verify there is leadership alignment and stakeholder buy-in as the project progresses. 

Financial Management

· Adapt to financial policies and procedures. 

· Assist in determining proper and appropriate funding, if required. 

· Assist the project director or office controller in the maintenance of Client Information. 

· Assist the project director or office controller in the maintenance of Engagement Information. 

· Communicate and coordinate with the organization’s internal financial systems to facilitate invoice and payment processes. 

· Complete the Financial Plan and obtain the appropriate approvals. 

· Establish a payment tracking process and resolve any payment issues or inquiries. 

· Establish the Financial Baseline. 

· Establish the practices to validate time and expense tracking and monitoring. 

· Identify and incorporate any terms, conditions, and procedural processes established by the organization for project financials. 

· Identify suitable resources needed to control project financials. 

· Identify, track, and report on risks related to project financials. 

· Identify, track, and report quality metrics established for performance reports. 

· Implement formal performance monitoring practices required for the contract. 

· Implement informal performance activities to gauge future performance trends. 

· Implement or participate in any change control activities related to the contract, including identification, analysis, justification, and approval. 

· Monitor the status of accounts receivable. 

· Obtain appropriate approvals for the Budget Strategy.

· Obtain appropriate approvals for the Financial Plan. 

· Prepare and assist the office controller in the preparation of bills and invoices. 

· Prepare and submit Time and Expense Data. 

· Provide financial justification for the project. 

· Review the Financial Plan with the appropriate project management and organizational management. 

· Track the progress of the Financial Plan.

Validate compliance to time and expense policies and procedures by project members.

Integration Management

· Analyze Integrated Project Plan Variances.

· Assign responsibility for recording workplan actuals for scope, cost, and time.

· Audit individual team members’ progress reports.

· Conduct or delegate the responsibility of facilitating the meeting where project dependencies are identified. 

· Determine which project completion issues need to be referred to the issues management process.

· Develop the Project Integration Strategies. 

· Identify and resolve integration issues. 

· Identify any outstanding commitments from or to vendors. 

· Identify project completion issues. 

· Identify tools, methods, and workplans that require integration.

· Include closeout activities in the team workplans and incorporate closeout activities into the Integrated Project Plan. 

· Perform the responsibilities of a knowledge coordinator, including writing the engagement summary and preparing sample deliverable descriptions for use on future projects.

· Produce Performance Reports for the project periodically and as required. 

· Provide documentation of project deliverable completion and acceptance. 

· Recommend corrective action.

· Review list of materials to be included in project archives for completeness. 

· Review the Integrated Project Plan. 

· Take the lead in the issue resolution process and identify project priorities when resolving issues. 

· Verify that appropriate project-wide assumptions have been established for use by the teams in constructing their workplans.

· Verify that appropriate team workplans are included in the integration process. 

· Verify that closeout activities are included in the team workplans and incorporated into the Integrated Project Plan. 

· Verify that teams and team leads are aware of the activities under their influence that comprise the Integrated Project Plan critical path.

Verify that the integration of appropriate project workplans. 

Logistics Management

· Arrange for conditioning, packing, and shipping of the logistics resource. 

· Assist in determining the proper and appropriate funding. 

· Carry out or commission any necessary inspections or testing of the received products. 

· Carry out or commission the evaluation of products and suppliers. 

· Communicate any significant costs, disruptions, or discrepancies with the decommissioning of logistics resources to the project director. 

· Complete the Acquisition Requisition and verify that it contains appropriate approvals.

· Continually review logistics needs and make appropriate adjustments. 

· Delegate to appropriate personnel the responsibility to decommission resources. 

· Develop a decommission plan to deinstall, remove, or return logistics resources. 

· Develop plans to commission the acquisition, installation, and maintenance of logistics resources.

· Identify individuals and groups to interview; collect the requirements. 

· Identify logistics resources no longer needed for the project. 

· Identify suitable products, services, and suppliers to meet requirements. 

· Identify, track, and report on quality metrics established for this task. 

· Inspect or review the resources to verify the resource availability and suitability. 

· Interview executives, managers, and staff to collect the requirements. 

· Justify the acquisition.

· Maintain records of the acquisitions and the quality controls applied. 

· Plan, execute, and control quality processes, including the use of questionnaires, surveys, or samplings. 

· Plan, execute, and control the external activities for the environment preparation. 

· Plan, execute, and control the installation, maintenance, and testing of goods and services. 

· Plan, execute, and control the organization’s activities for decommissioning logistics. 

· Plan, execute, and control the organization’s activities for the environment preparation. 

· Plan, execute, and control the staff support for the goods and services. 

· Prepare and report the status of staff support and any actions being taken or anticipated against the staff support. 

· Prepare and report the status of the goods and service and any actions being taken or anticipated against the goods, services, or supplier. 

· Provide feedback about the supplier to relevant authorities. 

· Receive goods and generate goods receipt transactions. 

· Return faulty goods with necessary notifications. 

· Review and approve invoices to indicate goods or services received and to initiate the payment process. 

· Review and approve invoices.

· Review and approve the functional testing for the goods or services. 

· Review approvals for individual expense resources. 

· Review Procurement Contracts for specific terms and conditions.

· Schedule resources and create a workplan for preparing the Logistics Plan. 

· Specify the requirements for the requested product and service. 

· Track the progress and performance of staff support related to the goods and services. 

· Track the progress of acquisitions and deliveries. 

· Track the progress of decommissioned resources.

· Track the progress of the environmental preparation and functional evaluation of the goods or services. 

· Update the list of logistics contacts. 

· Verify that a Purchase Order is complete and routed to the selected supplier. 

· Verify that final payments are made to suppliers or internal accounts.

· Verify that functional testing procedures are prepared and appropriate. 

· Verify that small acquisitions are completed and the proper acquisition expenses are processed. 

Verify the logistics resource is returned in a fair and reasonable condition.

Organization Management

· Approve planned team-building activities. 

· Approve the scheduled team-building activities and the planned performance-improvement activities. 

· Approve the training plan. 

· Brief senior management and obtain approval before officially decommissioning staff. 

· Complete the Roll-On Package for each team member.

· Conduct project team orientation.

· Construct the Project Office Profile. 

· Contact candidate staff who have been selected to the project team.

· Coordinate with any other team leads for skill or staffing requirements.

· Coordinate with project executives for the appointment of the management team. 

· Define roles and responsibilities. 

· Define the organizational strategy and the organizational breakdown structure. 

· Define the responsibilities of the project controller and tailor these responsibilities to the role of the project office. 

· Define, establish, and obtain approval for the project office’s role. 

· Delegate project office responsibilities to specific support staff. 

· Develop a process for periodically auditing or reviewing the effectiveness of the project office. 

· Develop and implement policies and procedures. 

· Develop the staff Roll-Off Schedule. 

· Evaluate performance reviews. 

· Evaluate the project’s dependency on each resource. 

· Identify available resources for the project management team and administrative support. 

· Identify available resources.

· Identify changes (if any) to the Procurement Plan.

· Interview and select the project management team and administrative support team members. 

· Interview candidate staff (if necessary).

· Make final staff selection.

· Notify each resource of his or her finalized roll-off date. 

· Plan and execute the integration of each resource into his or her organization, including making necessary arrangements to promote a smooth transition. 

· Responsible for performing the following duties of the knowledge coordinator:

· Coordinate with the Knowledge Manager for the Industry or Service Line. 

· Facilitate Lessons Learned. 

· Learn knowledge resources, such as KNet, research services, and websites. 

· Update engagement summary. 

· Prepare sample deliverables descriptions for use on future projects. 

· Write engagement summary. 

· Review candidate staff resumes and Career Development Plans (CDPs).

· Review each resource’s project goals in preparation for setting the resource’s roll-off date. 

· Review inputs to this task to understand the staffing requirements, contractual obligations, and project constraints (cost, time frame).

· Scope the responsibilities of the project office. 

· Select candidate for project staff.

· Set a target roll-off date for each resource. 

· Set up or oversee that the project office processes are implemented. 

· Update the Procurement Plan (if necessary).

Verify compliance with the team development plan, the staff performance improvement plan and the performance evaluation procedures. 

Procurement Management

· Adapt to procurement policies and procedures established by the procurement authority. 

· Assist in any dispute strategies or activities. 

· Assist in dispute negotiation, arbitration, or litigation. 

· Determine the appropriate formal and informal Schedules to manage the engagement contract. 

· Determine the Responsibilities, including the individuals responsible for the management of the engagement contract. 

· Determine the scope of events and the processes to effectively manage the engagement contract. 

· Develop a quality plan and a risk plan for the contract. 

· Implement or participate in any change control activities related to the contract, including identification, analysis, justification, and approval. 

· Implement the proper incentives outlined by the project director to verify that the scope of the Client Contract and the Client Contract Management Plan are followed. 

· Meet with organization and Deloitte management to fully understand the key features of the engagement contract. 

· Monitor and report to management any expected disputes with the contract. 

· Prepare fact analyses on dispute issues for management. 

· Prepare the Client Contract Management Plan. 

· Prepare the list of key component and requirements for the Client Contract. 

· Review the engagement contract.

· Verify that communication between the organization and the project team is timely, effective, and appropriate. 

· Verify that communication between the supplier and the project team is timely, effective, and appropriate.

· Verify that the Client contracts Administration Log is complete, archived, backed up, and recoverable, if necessary. 

· Verify that the Client contracts Administration Log is up-to-date and usable.

· Verify that timely feedback is prepared and delivered to the organization.

· Adapt to procurement policies and procedures established by the procurement authority. 

· Assist in any dispute strategies or activities. 

· Assist in determining the proper and appropriate funding for the procurement. 

· Assist in dispute negotiation, arbitration, or litigation. 

· Assist in examining and evaluating the supplier response to verify that it meets the request requirements. 

· Assist in the transition from establishing the contract to administering the contract. 

· Assist the procurement authority with developing the strategy for the contract method, contract type, or other procedures related to preparing the supplier request. 

· Define the Statement of Work and Specifications for the requested goods and services. 

· Develop a quality plan and a risk plan for the contract. 

· Develop the Procurement Plan and verify that the plan is approved by the appropriate individuals. 

· Establish a payment tracking process and resolve any payment issues or inquiries. 

· Identify any terms, conditions, and procedural processes established by the organization for the procurement. 

· Identify suitable products, services, and suppliers to meet the established procurement requirements. 

· Identify, track, and report the quality metrics for this task. 

· Identify, track, and report the risks related to the procurement. 

· Implement formal performance monitoring practices required for the contract. 

· Implement informal performance activities to gauge future performance trends. 

· Implement or participate in any change control activities related to the contract including identification, analysis, justification, and approval. 

· Justify the procurement. 

· Monitor and report to management any expected disputes with the contract.

· Monitor the progress of the RFP, RFQ, IFB, or RFI. 

· Participate in contract negotiations. 

· Perform quality reviews and risk reviews; make the necessary corrections. 

· Plan, execute, and control the quality processes using questionnaires, surveys, or sampling. 

· Prepare and participate in any bidder conferences or question and answer sessions with the supplier. 

· Prepare fact analyses on dispute issues for management. 

· Prepare the evaluation criteria for the procurement products and suppliers. 

· Recommend to project management the supplier to which to award the contract. 

· Review and incorporate any procurement policies and procedures established by the procurement authority. 

· Review the Procurement Plan with the appropriate project and organizational management. 

· Track the progress of the Procurement Plan. 

· Verify that communication between the supplier and the project are timely, effective, and appropriate. 

· Verify that the Procurement Contract Administration Library is complete, archived, backed up, and recoverable, if necessary. 

· Verify that the Procurement Contract Administration Library is up-to-date and usable. 

Verify that timely feedback is prepared and delivered to the supplier and owning authority. 

Quality Management

· Develop the Quality Management Plan with assistance from the team leads. 

· Identify, document, and communicate the deliverables review process to the project team. 

· Support quality processes within the project. 

· Manage ongoing quality control. 

Participate in quality issue resolution. 

Risk/Issues Management

· Actively participate in the steps in this task, including identifying, categorizing, prioritizing, and quantifying risks, as well as developing mitigation strategies. 

· Assign project staff to follow-up activities for Risk Mitigation Strategies. 

· Determine which organizational units the project risks affect. 

· Determine which risk mitigation plans should be implemented. 

· Organize the project risk planning process. 

· Set up the risk review sessions. 

· Verify that any newly identified risks or Risk Mitigation Strategies are documented appropriately. 

· Verify that risk mitigation strategy assignments are clearly documented and become part of the project workplan, where appropriate. 

· Verify that the effectiveness of each Risk Mitigation Strategy is reported. 

· Verify that the team member assigned to each implemented risk mitigation plan performs the following: 

· Execute the Risk Mitigation Implementation Workplan 

· Monitor the status of the implemented risk mitigation plan 

· Report any changes in the probability of occurrence and potential impact of each risk 

· Analyze and document the success and failure of the Risk Mitigation Implementation Workplan 

· Update any necessary issues, logs, or other documentation 

· Determine a schedule for the Risk Mitigation Implementation Workplan 

· Approve issues for analysis. 

· Approve proposed issue resolutions for execution. 

· Assign resources for issue resolution. 

· Assign the issues to issue owners. 

· Categorize issues. 

· Close issues.

· Communicate the issues management process defined in the Issues Management Plan to the project team. 

· Communicate the status of issue management activities to project team members and organization stakeholders. 

· Define issue priority. 

· Define the process for identifying and documenting the need for change in a project. 

· Develop the Issues Management Plan with the assistance of the project controller (as applicable) and the organization’s project director or sponsor. 

· Develop the Project Scope Statement. 

· Escalate or expedite changes for resolution.

· Escalate or expedite issues for resolution. 

· Establish the Issues Follow-Up Process. 

· Establish the mechanisms to verify that each project team member reviews and understands the Project Charter. 

· Expedite or escalate issues. 

· Identify and integrate other project and initiative requirements into the Work Breakdown Structure. 

· Identify the Constraints, Assumptions, and Critical Success Factors and develop the Risk Strategy 

· Statement for the project. 

· Prepare and communicate issue resolution status. 

· Review the issue resolution actions for appropriateness and timeliness of execution. 

· Review the issue resolution schedule and verify that has a minimal effect on the project schedule. 

· Review the status of issues and evaluate their progress.

· Submit the completed Issues Management Plan to the project directors for approval. 

Verify that issue owners adhere to the procedures and protocol defined in the Issues Management Plan. 

Scope/Change Management

· Act as the focal point for project communications and change requests.

· Advise and recommend action to the change control board. 

· Aid in the identification of the goals, objectives, and stakeholder expectations. 

· Align the goals, objectives, and stakeholder expectations with the contract criteria. 

· Approve changes for analysis.

· Approve proposed change resolutions for execution.

· Assign the change requests to change owners,

· Assign resources for change request resolution.

· Assign the issues to issue owners. 

· Categorize issues. 

· Define change request priorities.

· Define the process for identifying and documenting the need for change in a project. 

· Develop the Project Scope Statement. 

· Escalate or expedite changes for resolution.

· Establish a method for classifying and recording change requests.

· Establish and obtain the organization’s written agreement for change request follow-up activities.

· Establish the escalation and expediting procedures. 

· Establish the mechanisms to verify that each project team member reviews and understands the Project Charter. 

· Expedite or escalate change requests.

· Identify and integrate other project and initiative requirements into the Work Breakdown Structure. 

· Identify the Constraints, Assumptions, and Critical Success Factors and develop the Risk Strategy 

· Statement for the project. 

· Interview key stakeholders when collecting the required information for the Project Charter. 

· Perform the necessary research for creating the Project Background. 

· Prepare and communicate change request status. 

· Prepare the Deliverables Review Process. 

· Prepare the Executive Summary. 

· Prepare the integrated Work Breakdown Structure. 

· Prepare the milestone chart, budget, organization chart, and other approach materials for the project. 

· Prepare the Project Information. 

· Prepare the Scope Management Strategy. 

· Present the Executive Summary to the project board for review and approval.

· Provide direction and guidance to the Project Team in the preparation of the team’s Work Breakdown Structure. 

· Review and update the Project Charter, as needed. 

· Review status of the Change Request Log and changes and evaluate their progress. 

· Review the change request actions for appropriateness and timeliness of execution. 

· Review the Change Request Log. 

· Review the change resolution schedule and verify that it has minimal effects on the project schedule.

· Review the Integrated Project Plan. 

· Review the Workplan.

· Update the project baseline according to approved change requests.

Verify that the change owners adhere to the procedures and protocol defined in the Change Management Plan.

Workplan Management

· Avoid "scope creep." 

· Identify dependencies between activities in the WBS.

· Create and refine the WBS. 

· Decompose the WBS into work packages. 

· Develop an activity list for each WBS item.

· Establish the Project Baseline. 

· Estimate activity duration. 

· Identify Milestones. 

· Identify Resource Requirements. 

· Obtain approval of the Workplan. 

· Optimize the Workplan for constraints, resources, critical paths, and activities.

· Review the Workplans of others.

· Sequence the activities in the WBS. 

© 2004 Deloitte Consulting
11
RoleAttach_ProjectManager.doc

[image: image1.png]