## Slide 1: CRM Definition Phase - (Revised) WP1 Siebel Only and Postponed BroadVision Solution
Final Draft
30th November, 1999

## Slide 2: Preface
At a meeting with X on 29 November, Deloitte Consulting was asked to revise its project costing to reflect a ‘Siebel only’ solution for WP1 to be delivered at the end of March.
This revised CRM Definition Phase document reflects the business capabilities that would be within Deloitte Consulting’s remit to deliver and other considerations of a ‘Siebel only’ implementation.
A ‘Siebel only’ solution would provide Siebel functionality with integration to the business systems, as defined in this document, and specifically postpones the following:
  the implementation of Broadvision
  the web-enabling of Siebel (NB:Siebel’s web-enabled Communications solution will not be available in time to meet Company X’ requirements for 31 March 2000)
  the delivery of any business systems information to the web interface
  the implementation of web-based security and authentication (particularly for UM).
The implementation of a ‘Siebel only’ solution will enable Company X users and partners to access Siebel functionality directly, if required.
It is assumed that Company X will commission the required web-related features necessary for launch through a separate project (based on BlueStone). This BlueStone project and the integration of the Siebel and BlueStone systems are explicitly out of scope, as is the routing of customer contact via any other channel into Siebel, e.g. telephone.
Furthermore, the management of documents delivered via the web (e.g., via Documentum) is excluded the project scope. The implementation of Documentum or any other DMS is subject to a decision by Company X on when to implement.
We have however, provided an estimated project cost for a subsequent migration to BroadVision.

## Slide 3: Contents
Objectives
Confirmation of Business Capabilities supported 31 March
Extension of Solution to support UM 30 April
Confirmation of Interfaces between Business Systems and CRM
Implications of BlueStone Pilot
Project Approach
Team Structure and Project Cost
Appendix

## Slide 4: Objectives
A CRM Solution Discussion document, dated November 17, proposed a CRM solution and implementation approach.
Based on this document, Deloitte Consulting was asked to undertake a six day definition phase. This phase had the following objectives:
  To confirm the functionality to be delivered in each phase (or work package) of the CRM project. This includes confirmation of the functionality which is required (and which is feasible to deliver) by 30 April 2000 to support the launch of Unified Messaging services.
  To validate the integration points with the business systems applications, following the recent confirmation that Kenan (Billing and Order Management) and Remedy (Trouble Ticketing) will be incorporated within the application architecture.
  To provide further information on how the integration between Siebel and BroadVision will be achieved.
  To design the CRM team structure, providing skill profiles for team members, and highlighting how this team integrates with the existing Business Systems project team.
  To develop the CRM workplan which is integrated with the Business Systems workplan.

## Slide 5: Activities Performed
Analysis of functional requirements for March 31 including
  identification of package delivering the requirement
  identification of interface dependency
  customisation effort required
Selection of specific functional requirements to be delivered in work package 1 and the extension of work package 1 for Unified Messaging
Analysis and definition of integration points between CRM and Business Systems
Validation of integration points with Business Systems package configuration and integration architecture teams
Development of BroadVision and Siebel integration approach
Review of Implications of BlueStone pilot on proposed approach
Development of CRM project plan
Development of CRM team structure and resource skill profiles
Review of CRM Definition phase deliverable with Company X management
Revision of CRM Definition phase deliverable to reflect a ‘Siebel only’ solution
The following activities were undertaken to meet the objectives of the CRM definition phase:

## Slide 6: Contents
Objectives
Confirmation of Business Capabilities supported 31 March
Extension of Solution to support UM 30 April
Confirmation of Interfaces between Business Systems and CRM
Implications of BlueStone Pilot
Project Approach
Team Structure and Project Cost
Appendix

## Slide 7: Confirmation of Business Capabilities
Work package 1, “Web CRM and Partial Back Office Integration”, will be delivered on 31 March 2000. This work package is:
targeted to the base products (VPN, IDD, transit, bandwidth, Fax over IP (TBD))
targeted to Company X’ Partners
allows Company X partners to access CRM functionality on the WEB via integration of Siebel and BroadVision
integrates with Billing, Order Management and Trouble Ticketing
Business Capabilities for Unified Messaging are supported by adding an interface to the UM platform and validating that the processes implemented in work package 1 support UM.
The extension of work package 1 for 30 April 2000 does not include embedding UM specific business rules and processes in the CRM solution, but does ensure that the solution delivered for 31 March does support the UM rollout.
Based on the prioritised functional requirements list produced during the CRM study project, and further discussions with Company X the following represents the understood Business Capabilities for WP1 and UM extension and possibly for WP2
Work package 2, “Web CRM”, will be delivered after 31 March 2000. This work package is:
allows Company X partners to access CRM functionality on the WEB via integration of Siebel and BroadVision
allows direct access to Billing from BroadVision
migration from BlueStone to BroadVision
interface from BroadVision to a Document Management System
The business capabilities described on the following pages, highlight capabilities delivered in WP1 in bold and those additional capabilities delivered in WP2 in gray

## Slide 8: Business Capabilities - Marketing
Partners and customers will be able to access documents relating to Company X’ products via the Web. The Web is used for document distribution. A Document Management System will support the administration and creation of material.
A range of product literature and other related documents (in English) are available and orderable via the Web for customers, account managers, sales reps and partners
Competitive and marketing intelligence is broadcast via the web site to partners and sales representatives.
The following document types concerning Company X and the basic products will be published:
  text, brochures, pictures, images for promotion, release news, company news (in documentum)
  Product catalogue and price lists provided from Siebel
Access to marketing material documents (in documentum) is based on pre-defined authorisation profiles (e.g. partners, preferred partners, customer, sales-rep, account manager etc.)
The material placed on the Web is searchable using keywords
A Document Management System will provide the basic capabilities for document creation, imaging and administration

## Slide 9: Business Capabilities - Sales
Opportunity Management - Provides comprehensive opportunity management functionality including up-to-the-minute, shared information about accounts, sales funnel, contacts, notes and activities
Product Configuration - Customers, partners will be able to configure standard base products over the web based on the product catalogue, pre-defined forms and supporting business rules. WP1 will not extend to intelligent configuration that will proactively offer suggestions
Pricing - Products will be priced upon the individual components and configuration. Discounts for WP1 will be handled manually
Quotes & Proposal – allows partners and account managers the ability to develop draft quotes and sales proposals, verify, submit and revise, tailored to meet customer requirements and provide completed proposal and quote via the web. Company X will approve these quotes and proposals prior to issuing to the customer
Business Rules for “Authorisation” allowing key people in Company X to validate/issue definitive proposal to partners and clients.
Provide opportunity management, product configuration for the base product portfolio, pricing and quote & proposal capabilities.

## Slide 10: Business Capabilities - Usage and Customer Service
Partners & customers will make use of the Web for service requests and will be navigated to support and service material. Partners will enter and track service requests and Trouble Tickets via the Web.
Partners entering service requests will be guided to support material (FAQ) on the Web
Partners will be provided with access to customer service center via a “Call Me” procedure (WP1 - No CTI rather email or web notification in service centre)
Partners will access images of current bills and payment status via the Web coming from DMS/Kenan
A history of bill images will be published via the Web and provided to partners and customers
Partners will be able to feedback and make inquiries concerning billing and payment. They will also be able to analyse and download service usage reports for querying purposes
Authorisation mechanisms will ensure the required levels of security and privacy.
Company X and partners will have an Integrated view of trouble tickets managed in Siebel and Remedy

## Slide 11: Business Capabilities - Provisioning
Order Entry and Provisioning information will be enabled via Siebel, accessible through the Web. Customers and partners will be able to access the orders and provisioning status via the web.
Customers and partners will be able to order products and services through the web site and review content on-line
Orders that are not captured in Siebel will be processed manually in Order Management and Provisioning
Partners are able to access provisioning information related to current and previous orders and track provisioning status via the web (WP1 will not enable dynamic changes to bandwidth, through a Bandwidth Manager)
Provisioning information is accessed from the Order Management System ensuring consistency and providing partners with overall picture of order status
Authorisation measures and infrastructure ensure the required, high level of security with respect to self-provisioning
Web-based provisioning requests are captured in Siebel ensuring seamless processing and integration with Order Management and Provisioning

## Slide 12: Business Capabilities - Order Management
CRM will provide Order Management with a validated CRM product order
Order Management will provide CRM with order status information to enable visualisation on the web
Order Management will feedback information about validation, flexibility, events and check reporting to Siebel
Order Management will provide order work flow procedures by interfacing with CRM.

## Slide 13: Business Capabilities - Retention & Termination
Provide customers with ability to request to discontinue base product services via the web interface pending Company X approval
Provide customer with status and confirmation of discontinuation request via the web
CRM will capture rationale for discontinuation of all base product services, alert Company X and update customer profile (WP1 will not dynamically generate implications and offer alternative pricing based on pre-defined rules)
CRM will enable customers, sales professionals and account managers to discontinue a service from the base product line

## Slide 14: Business Capabilities - Other Channels Management
Provides ability for customers and partners to request a call from the service centre via a “call me” button on the web site (e-mail/web based notification not CTI in WP1)
Provide contact management capabilities for administration of interaction with customer, partner or sales person
Provide the service centre, Sales and Marketing with direct access to
  Customer master data
  Current and past order history
  Service requests and trouble tickets
  Order entry capability
  Sales and Marketing data
  Service data - usage, reporting, etc.
Provide Company X with the ability to support customer and partner interaction through the voice channel. Support is based upon out-of-the box CRM Package capability.

## Slide 15: Business Capabilities - Community & Site Mgt.
Allows management and configuration of electronic user profiles to form the basis for future profiling and personalisation
Allow organisation and classification of content for display on a Web site
Enables users alert notification when new or updated content matching their interests (e.g. product news, competitive intelligence)
Provides content management capabilities so that a content management process for publishing information on the web is supported
Provide web users (customer, account managers, partners and employees) with a high level of security and privacy concerning data and information via the web by utilising authentication, encryption and non-repudiation mechanisms
Provides user observation and reporting capability
Provide customers the ability to navigate the Company X web site in a simple manner and provide basic tools for community development. Provide Company X with out-of-the box content management capabilities and web activity reporting.

## Slide 16: Contents
Objectives
Confirmation of Business Capabilities supported 31 March
Extension of Solution to support UM 30 April
Confirmation of Interfaces between Business Systems and CRM
Implications of BlueStone Pilot
Project Approach
Team Structure and Project Cost
Appendix

## Slide 17: Extension of WP1 to support Unified Messaging
As defined in the CRM solution discussion document of 17 November, work package 2 contains the implementation in the CRM solution of the unique business processes and business rules required to support the Unified Message business model.
Given the UM business case, it was suggested that the size of the UM market in the first year did not justify the cost of a dedicated approach to UM and the implementation of work package 2. Rather, the implementation of work package 2 could be shifted to such a time when the size of Company X’ UM market justified the cost of implementation.
However, as Company X plans to rollout UM on 30 April 2000, it is important to validate that the CRM solution in work package 1 supports that rollout.
The extension of work package 1 to support UM specifically addresses how to support the rollout without the implementation of UM specific business processes and business rules in the CRM solution.
The additional business capabilities to be delivered in this extension are outlined in the pages that follow.

## Slide 18: WP1 Extension to UM
Marketing
Extend product catalog with UM product details. Provide end-user ability to self-configure UM service based on personal requirements via the web.
Provide customer and partner ability to configure UM service and view payments and bill via web site (Bill payment will not be enabled via the web)
Extend opportunity management and proposal generation to account for UM customers and prospects
Sales
Documents and support material concerning Unified Messaging are available for partners, account managers, sales reps and customers including SMEs.
Add UM competitive information to CRM and distribute to corporate customers via web
Extend navigation capabilities to UM related material

## Slide 19: WP1 Extension to UM
Usage and Customer Service
Service requests concerning UM will be resolved via the Web. Corporate customers (not end users) will be able to access UM billing images and track payments.
Provide corporate customer with the ability to amend, change and review their UM set-up details as and when required
Service request support material on the Web will be enhanced to include UM
Customers will enter UM service requests via the Web and will be able to track the UM request life-cycle
Corporate service requests will be consolidated in Siebel and provide an overall picture of service requests and their status to the partners
Corporate UM customers will be provided with access to customer service center via a “Call Me” procedure
Order Management
UM platform will be interfaced to OM and/or Provisioning which will provide requested messaging services

## Slide 20: WP1 Extension to UM
Provisioning
Retention & Termination
Corporate customers can access UM provisioning information via the Web
Corporate customers can update provisioning of UM related services (self-provisioning) given a set of defined conditions
Web-based UM provisioning requests are captured in Siebel ensuring seamless processing and integration with Order Management and Provisioning
Provide customers with ability to request a discontinuation of UM services via the web interface
Provide customers with status and confirmation of UM discontinuation requests via the web
Allow customer complaints to be handled and tracked using Siebel
CRM will capture rationale for discontinuation of UM all base product services, alert Company X and update customer profile

## Slide 21: WP1 Extension to UM
Other Channel Management
Virtual Community & Site Mgt
Business capabilities of WP1 will account for UM telephone contact support needs for corporate contacts
Authorisation profiles and capabilities are enhanced to for corporate customers accessing services via the Web
Web-Navigation and the Web-Interface are targeted to support corporate customers and end customer needs with respect to UM

## Slide 22: Contents
Objectives
Confirmation of Business Capabilities supported 31 March
Extension of Solution to support UM 30 April
Confirmation of Interfaces between Business Systems and CRM
Implications of BlueStone Pilot
Project Approach
Team Structure and Project Cost
Appendix

## Slide 23: Logical Solution Architecture
Internet
Document
Management
Customer
Service
Imaging
Customer Relationship Management
Back Office Integration
System
Management
Tools:
Internet
Publishing
Business Objects
Telephony
Customer
Out of Scope
Web Services and Delivery
Intrusion protection
‘Company X Web Project’
Direct access, as required

## Slide 24: Interfaces between CRM and Business Systems
Cisco Network
Elements
Business Reporting Architecture
CRM Solution
Order Management
Interconnect
SAP R/3
Mediation
Circuit Inventory System
Provisioning
Syndesis
Kenan
Billing
Trouble
Ticketing
Cisco NetFlow
Remedy
Kenan

## Slide 25
CRM Application Architecture
Network Elements
Order Management
Billing
CPP
SAP
Mediation
Circuit Inventory
Provisioning
UM Repository
Trouble Ticketing (Remedy)
Web Enabling (BroadVision)
31 March
31 March
31 March
30 April
31 March
Out of scope
CRM (Siebel)
Out-of-Scope WP1 (Broadvision Extension WP2)

## Slide 26
CRM Application Architecture
Network Elements
(Cisco)
Order Management
(SAP PS & Kenan)
Billing
(Kenan)
CPP
SAP
CRM (Siebel)
Provide Trouble Ticketing and Service
Configure Products and Services
Sell services
Web enabling (BroadVision)
Sell services
Configure Products and Services
FAQ, Knowledge Repository, Communities, etc.
Provide Presentation and Personalisation
Mediation
(Xacct)
Circuit Inventory
(AI Metrix)
1, 5, 28, 39
9, 10, 12, 18, 31
2, 33
37, 38
Provisioning
(Syndesis)
UM Repository
(Activa UM 4.1+)
Handle orders
Bill services
Handle billing
Handle Trouble Ticketing info
Bill services
Handle billing
Programmer
Programmer
Trouble Ticketing (Remedy)
39
57
Handle reporting info
All numbers represent Interface Catalogue reference
number (see Business Systems deliverables)
Out-of-Scope WP1 (Broadvision Extension WP2)
Out of scope

## Slide 27: Contents
Objectives
Confirmation of Business Capabilities supported 31 March
Extension of Solution to support UM 30 April
Confirmation of Interfaces between Business Systems and CRM
Implications of BlueStone Pilot
Project Approach
Team Structure and Project Cost
Appendix

## Slide 28: Implications of BlueStone Pilot
Given a BlueStone Pilot, content developed for the pilot can be easily migrated to BroadVision. However, the migration to BroadVision of functionality requiring a single view of the customer would involve additional software redevelopment .
Web Application Server
Siebel
Business Systems
JSP
BlueStone
XML
XML
Web Application Server
BroadVision
Siebel
Business Systems
JSP
BlueStone
XML
XML
1
Redefine Web processes to integrate BroadVision capabilities
Rewrite code to connect Web pages to BroadVision.
2
‘Throw away’ BlueStone code for functionality due to direct integration of Broadvision and Web Application Server
3
Migration to Broadvision
3

## Slide 29: Implications of not implementing BroadVision in WP1
While much of the web front end made available through BlueStone can be migrated to BroadVision, some BlueStone development will need to be discarded in migrating to BroadVision
Implementing BroadVision will require additional development to connect to the web front end
Additional development work will also be required to integrate BroadVision and Siebel at a later date
Work packages 3 and 4, as previously defined, are no longer valid as they build on an integrated BroadVision and Siebel solution
Additional development will be required to integrate BlueStone and Siebel; this effort is not included in Deloitte’s workplan or budget

## Slide 30: Contents
Objectives
Confirmation of Business Capabilities supported 31 March
Extension of Solution to support UM 30 April
Confirmation of Interfaces between Business Systems and CRM
Implications of BlueStone Pilot
Project Approach
Team Structure and Project Cost
Appendix

## Slide 31: Approach and Company X Contribution
Sales & Marketing
Customer Care
Operational process vision and data ‘mapping’
Brown paper sessions on detailed real life business cases
Solution development review sessions
Intense week interviewing with key stakeholders from sales, marketing, customer services, NOC, etc.
Focused / almost full time attention of key figures from Company X
Workshops
Processes mapped to detailed solutions/modules
IndustryPrint best practices
Final agreement on the detailed scenarios and some key Siebel-specific GUIs (official documentation)
Review sessions for progressive alignment of the solution to the scenarios
Test
Training
Documentation
Rollout
Tiger Team with competence of:
industry specific processes, business rules, products, pricing and technical content of the proposal
experienced (2-3 years) package configuration from DC and vendors
data
proved system integration methodology and technology within CRM and with Business Systems
Customer, process and business capability driven
One Month
Two Months
One Month

## Slide 32: Siebel Implementation Timeframe
Factors reducing time to implementation
Company X does not have a legacy system environment, eliminating the need for a complex data mapping and data conversion exercise. As Siebel would be the master for customer data, no significant changes to the Siebel database structure needs to be made to support legacy customer data.
Company X would initially be loading a small number of customers, products and pricing models into Siebel. For work package 1, Siebel will enable standard configuration and pricing, eliminating the need to implement complex product catalogue structures and pricing structures.
For 30 March 2000, minimal customisations would be made to Siebel. The project approach would be to maximise the use of standard, out-of-the-box functionality available in Siebel’s Communications industry solution and only make changes where absolutely necessary to support Company X’ business objectives.
Deloitte Consulting’s IndustryPrints
Deloitte Consulting has pre-defined Communications industry processes embedding global best practices. These processes are mapped to Siebel’s application suite. By utilising these IndustryPrints, we can start with a working set of processes that can be tailored to meet Company X’ business objectives. As they are already mapped to Siebel, any changes required to Siebel are easily identifiable and can be minimised during the process design stage, as appropriate.
Implementing Siebel in a very tight time window carries implementation risks. However, there are several factors present in the Company X environment that enables us to reduce the time required to implement Siebel. Furthermore, the use of Deloitte Consulting’s IndustryPrints helps to provide a best practices based starting point for the process design phase.

## Slide 33: Siebel Solution - Benefits
A Siebel selection for CRM for 31 March 2000, has a number of key strategic and tactical benefits.
Allows Company X to benefit form inherent Communications specific marketing, sales and customer service processes that are embedded in the package
Pre built business logic and processes in package allow for more aggressive and risk adverse roll-out to meet 31 March deadline
Establishes tight control of sales process within Company X and partners
Siebel data model provides an integrated and unified view of the customer across CRM and business system processes
Supports Mannersman strategic wish to use Siebel across the group
Establishes a consistent and efficient sales process and sales tools from Day 1, and avoids ‘process bad habits’ being developed
Siebel’s proven training and reference material allows rapid education and effectiveness of account managers and partner sales professionals from Day 1

## Slide 34: Contents
Objectives
Confirmation of Business Capabilities supported 31 March
Extension of Solution to support UM 30 April
Confirmation of Interfaces between Business Systems and CRM
Implications of BlueStone Pilot
Project Approach
Team Structure and Project Cost
Appendix

## Slide 35: CRM Project Team Structure
Siebel Manager
CRM Partner
CRM Solution Architect
Project Partner
Richard Porter
Project Manager
Rich Pople
Process
Integration
Manager
Tina Iglio
Process designer (Customer Services)
Process designer (Sales & Marketing)
Package Configuration Manager
Hurley / Pople
4 configurators
1 vendor resource
Technology Integration Manager
Rob Schenk
Infrastructure Manager
Ton Klappe
1 infrastructure consultant
Integration Development
Tom DeWinne
2 integration consultants
1 data consultants
1 vendor resource
Integration Architecture
Marcus Muldoon
Change Manager
Anne Gauton
First Phase Tiger Team
The CRM project team structure leverages the existing team in place for Business systems.
The CRM project would add an additional 9 FTEs to the project

## Slide 36: Project Resourcing
Project Management Infrastructure
Partner: Fabio Troiani Haig Tyler
CRM Solution Architect: Maria Churchill
Process Team CRM to Business Systems Integration
Stephen Ward Interface Designer (TBD)
Giorgio Gristina Adapter Configurator (TBD)
Andrea Buratti (2 weeks)
Siebel Team Data
Giullermo Ruiz (Team Manager) Giovanni D’Onofrio
Parham Ghorban Siebel resource
Lisa Ma
Daniel Gobits
Ines Boronat
Siebel resource
This is our proposed CRM team. These resources can be confirmed once we receive approval to proceed from Company X. Pen portraits for these candidates are provided in the Appendix.

## Slide 37: Cost Estimates for Work packages
April 30
March 31
June 30
TBD
Project Management
Work Package (WP0)
~ X Mill. Euro for Implementation
License fees:
Siebel ~ 180k
Project Management included in other Workpackages
CRM (Siebel) and Partial Back Office Integration
WP1
UM Support
(same WP1
solution)
X Euro
Notes:
Quoted costs exclude technical infrastructure costs and post-implementation support.
License fees are informed estimates and are subject to Company X’ negotiation with Siebel and BroadVision
Quote for the migration to BroadVision assumes the CRM management structure is already in place for the UM extension.
Migration to
Broadvision WEB
CRM WP2
X k Euro for Implementation
License fees:
BroadVision ~ 170k

## Slide 38: Cost Estimates for Work packages 3 and 4 (to be confirmed at the end of WP1)
April 30
March 31
June 30
TBD
WEB CRM for UM/SME
WP3
Project Management
WP0
Advanced WEB CRM
Fully Integrated
WP4
X k Euro for Implementation
Project Management included in other Workpackages
X k Euro for Implementation

## Slide 39: Next Steps
Agree solution architecture
Obtain approval to proceed
Mobilise CRM team
Integrate CRM team and work with Business Systems

## Slide 40: Appendix - Supporting Material
  CRM Candidate CVs
  Project Plan

## Slide 41: Team CVs

## Slide 42: Siebel Configuration Manager Candidate
Guillermo Ruiz, Senior Consultant
Guillermo Ruiz is an experienced Senior Consultant from the CRM practice of our Texas office. Project experience includes:
Front End Development Manager for the implementation of Siebel Telecom Central at a major telecommunications provider. Responsibilities included:
Leading a team of 20 people (Deloitte consultants, client personnel, other consultants and developers) for the design and development of a call centre front end for large-scale order management and provisioning system which included 5 on-line interfaces, 15 back-end interfaces and over 100 screens.
Developing a comprehensive plan for the delivery of front end functionality.
Senior architect for the Siebel Telecom Central application.
Systems Architect for the implementation of Siebel Telecom Central at a major Telecommunications provider. Responsibilities included:
Participating in the development of an overall architecture for a call centre application, focusing on middleware technology which included CORBA (Orbix OTM), Workflow Management (InConcert) and data translation middleware (GEIS).
Designing and leading the development of billing and calling card interfaces using Object Oriented (OO) methodology which included C++ re-usable objects, Rational Rose’s Unified Modeling Language (UML) and a database abstraction layer.

## Slide 43
Steven B Ward, Sr Consultant (UK)
CRM Process Design Candidates
Experience Summary:
Several years of experience in e-Business in Telecom & Finance industries.
Experience consists of e-Business strategy, functional definition, process design and CRM system implementation
Part of Deloitte CRM Phase 1 team at Company X and member of proposal team.
Major clients:
BBC
British Telecom
Major Retail Bank
Reuters
Relevant Skills:
BroadVision Business Manager
Edify Applications Developer
Giorgio Gristina, Consultant (I)
Experience Summary:
3 years experience in process design, system functional design, and requirements definition, focusing specifically on customer service and sales force automation.
Primary focus in telecommunications industry.
Major clients:
Telecom Italia
Telecom Italia Mobile
Relevant Skills:
Call centre and customer services
Sales Force Automation solutions
Andrea Buratti, Sr Consultant (I)
Experience Summary:
Two years experience in CRM, CRM process design and system implementation.
Specialisation in the telecommunications industry.
Major clients:
Telecom Italia
Telecom Italia Mobile
Telco IS Solutions Provider
Relevant Skills:
Call Centre technologies
Business process reengineering

## Slide 44
Parham Ghorban, Consultant (USA)
Siebel Configurator Candidates
Experience Summary:
Extensive experience with Siebel implementations in several industries.
Experience consists of gathering business requirements, functional design, configuration, and testing.
Major clients:
Major US Energy utility
US Financial Services Consulting Firm
Bank of America
Relevant Skills:
Siebel Tools
MS SQL Server, VB, SQL, HTML
Daniel Gobits, Consultant (NL)
Experience Summary:
Technical education and background. 2 years experience in e-Business and related IT. Siebel and BroadVision trained.
Experience consists of customer needs assessment and functional design.
Part of Deloitte business systems and CRM team at Company X.
Major clients:
European Commission
Major Dutch water utility
Relevant Skills:
Siebel Tools, BroadVision Tools
Java, JavaScript, VB, HTML
Ines Boronat, Business Analyst (E)
Experience Summary:
Technical education and background. 2 years experience in programming.
Siebel and BroadVision trained.
Experience mainly in manufacturing industry.
Major clients:
Automotive corporation
Catalonian Institute of Technology
Relevant Skills:
Siebel Tools, BroadVision Tools
C++
Lisa Ma, Sr Consultant (USA)
Experience Summary:
Technical education and background. 5 years experience in systems development, deployment and testing.
Siebel trained. Experience in several industries including telecommunications.
Major clients:
International telco
Several financial services companies
Relevant Skills:
Siebel Tools
VB, HTML

## Slide 45
Giovanni D’Onofrio, Consultant (I)
Experience Summary:
Technical education and background. Previous experience includes database engineering, data warehousing and CRM implementations. Mainly in telecom industry.
Major clients:
Telecom Italia
Relevant Skills:
Oracle 7 & 8, MS SQL Server, Vantive, Clarify, Erwin, Oracle Designer 2000, IQ Objects, Oracle Discoverer, VB, and PL/SQL
Data Candidate
Haig Tyler, Sr Consultant (UK)
Experience Summary:
Technical education and background. Specialist in systems integration, working in the messaging, directories and security domains.
Experience in Telecom and related IT industries.
Part of Deloitte business systems team at Company X
Major clients:
RAF
UK-based electricity utility
Large Australian telco
Relevant Skills:
LDAP, PBX, X.400, X.500
CRM Infrastructure Candidate