## Slide 1: Phase 0 Final Deliverable
A presentation of implementation options for SMENION I
July 28, 2026
NOTE NO OFFICIAL PROPOSAL WAS PRESENTED – THIS PRESENTATION REPRESENTS AN INITIAL 3 WEEK ASSESSMENT

## Slide 2: Business Drivers & Strategic Goals
Launch IP and Telephony services into an new customer base the small to medium-sized enterprises (SMEs) in the German market
Introduces a new technology, wireless local loop to enable service to those customers
Enter a new sales delivery channel using partner indirect sales agents to sell and service this new customer base
  Provided the partner company with a seamless and automated channel to enter orders and track prospects
Offer a suite of competitive products and innovative services to this market
  Competitively priced Voice and data products (email, web hosting)
  Build a stable foundation for new services (ASP, video conferencing and data and media streaming)
  Provide a flexible customer self-care service to build customer loyalty
Beat the competition (Enron Communications, FirstMark Communications, MCIWorldcom) who are also planning to offer services for this attractive market:
Internal
  Define a possible next-generation system support stack for other arms of the business
  Reduce the reliance on manual, slow, error prone processes
  Migrate to a new technical infrastructure
To provide Company Z with a selection of feasible implementation options for business systems and interfaces to support SMENION I and provide a strong and stable foundation for SMENION II.

## Slide 3: Statement of Work
Constraints
  Siebel and Arbor are fixed and no comparison or evaluation of other products are required
  Launch is fixed at 30 September
Phase 0 Scope included:
  System Stack to for direct access products FON and IP, based on the following major components:
    Siebel for Sales, Order entry, Customer Relationship Management, and web-front ends
    Kenan Arbor BP for Billing
    Workflow System Staffware
    Middleware BEA Tuxedo/CORBA
    Production platform SUN HW, SUN Solaris OS
    Databases preferably Oracle 8i
    Other components (e.g. Order Management, Trouble Ticketing & Tracking) to be defined by the integrator
Phase 0 Deliverables
  Out-of-the box Siebel Modules
    List of all Siebel modules which need to be deployed during phase I and phase II of the project. For all Sales Processes and products, Order and Provisioning Processes, Customer Care Processes
    A list of what required functionality could not be supported by uncustomised Siebel Modules
    Alternative Solutions to customised Siebel
  A complete list of necessary/recommended Modifications to Siebel:
    Data model, Screens, Workflow System, Code
    Our approach and methodology to Source Management
  Version Control and parallel development
    Definition of the Release Planning
    Our approach and methodology to Configuration Management
    Our approach and methodology to parallel development and releases
Deloitte Consulting has been asked to provide Company Z with an architecture, approach and feasible implementation plan to support the SMENION I launch of 30 September and provide a strong and stable foundation for SMENION II launch in early 2001.

## Slide 4: Assumptions
General:
  30. Sept. is go live
  Forecast end 2000: 600 customers with 1000 locations
  SMENION I does not support leased line product
  There will be no usage collection or rating for IP products in SMENION I
  There will be a completely new system stack and all applications will be based on Sun Solaris
  Network development for: provisioning, activation, collection and mediation solutions are not in the scope
  interfaces to those applications are in scope
Operational
  Development will be performed and completed in the Deloitte Consulting Solution Centre in Bath
    Company Z will be responsible for setting up testing, training and production environments in Germany
  The Development team will be led by Deloitte Consulting and will include resources from Company Z
Functional:
  Web presentation
    Customers (product information, coverage, e-mail setup, order status, trouble ticket status)
    Partners (product information, coverage, order entry, order status, VIGIS information)
  Customer care
    Fully operational at 30.9.00
    There will be a handover to BCCC:
      Trouble Tickets (level 3)
      Complete services after hours
  Billing
    Billing will be implemented using Arbor version 9.1
  Workflow
    Network will develop their own instance of Staffware to handle the network workflow
    Phase I of SMENION will provide an interface (either manual or automated) to the network‘s instance of Staffware
  Credit checking:
    is performed after order entry as the last step before the provisioning workflow starts.
    Customer checking will be moved forward in the process as far as possible

## Slide 5: Key messages and Constraints
SMENION I is a compromise product, the true strategic objective is SMENION II
SMENION I be offered only to a limited number of customers
The SMENION system stack should leverage any and all development work done to date in other business unit support stacks
Development support. No development facility will be provided in Munich
  The proposal that Deloitte will provide a development environment
Time. The existing dead line of 30 September leaves
  only 20 working days for detailed specification and configuration
  and a subsequent 20 working days for interface development
    Testing will be impacted
Content.
  No documented requirements exist for the:
    Mail Server integration
    IP Provisioning & Activation
    Collections
    Credit Checking
  No special configurations or modifications in support of those areas will be possible in the initial release
Organisational Structure & Governance
  The tight schedule will not permit time for ‘Abstimmungsgespraeche’
You’ve Said…
Constraints

## Slide 6: Proposed Solution Architecture
The proposed architecture was prepared based on the business requirements of the SME market and constraints of the greatly abbreviated timeline. Integration priority was placed on a seamless order enter and order status capability
Simplified Siebel-based solution for web presentation
Siebel to perform ‘Order Management’
Staffware to perform ‘Network Workflow’
Interface to Customer Data Validation engine(s)
Web-enabled Invoice View
Customer and Account Data owned by Siebel, replicated to Arbor
Leveraging existing solutions for Invoice production
Products, Rates & Discounts Owned by ArborBP

## Slide 7: Option 1 - Launch 30 September – Foundation Systems only (part A)
Designs and requirements frozen by 14 July
Configuration and development would begin not later than Monday, 17 July
Manual processes and file-based solutions would be developed for non-automated interfaces
NOTE: The proposed solution architecture does not require an interface for web-presentation to the dealers
All required interfaces for SMENION I (see next page A) would be developed and delivered by start of business Monday, 8 January 2001
RECOMMENDED
Knowledge
DB

## Slide 8: Option 1 – RE-Launch 8 January– Foundation Systems Full-Integration (part b)
Complete system stack integration
Integrated CTI, IVR and ACD
Integration of IP Usage through to billing and new product packages*
  Assumes an IP solution is known prior to 1 October 2000
Fully integrated Mail Server
Richer, more functional web-presentation, Dealer/Partner Management through BroadVision or eSiebel
Optional reporting engine and portal for the business and dealers (Reporting Repository)
January 2001
January 2001
Knowledge
DB

## Slide 9: Option 1: ALL MANUAL!!! Why would we choose to do this?!
Meets marketing and strategic goal to beat the competition to market
Ensures stable configurations from which to develop robust interfaces
Provides an opportunity to develop a integration solution that meets Company Z CORBA standards and works with the pre-selected systems in the stack
  e.g. Siebel
  Supports necessary Middleware analysis and development
Allows the system users to learn the processes and an hence perform better in the automated environment
Allows sufficient time for thorough testing and training to ensure a smooth launch
The dealers and the market won’t know the difference
  Web-enabled order entry
  The timeline necessary to physically provision and activate a customer will mask internal manual process
January release will include enhanced functionality to support some SMENION II requirements
Stability and Risk Reduction. The major risk is that you will be here anyway, but not by choice. This project is extremely late. Requirements are still in flux and the Network and other support systems are further behind. The new IT-standard for interfacing (BEA-WebLogic) has never been implemented in a production environment, as currently specified it won’t work with Siebel and it is largely supported by external resources.
Heavy manual support requirements
Parallel development activities
  Production systems, bug fixes and change requests
  New development for interfaces
Potentially delays the development of full SMENION II
Benefits
Risks
RECOMMENDED

## Slide 10: Option 2 - 30 September Launch– Foundation Systems Limited Integration
Requirements frozen by 10 July, design documents signed off by 21 July.
Configuration and development would begin not later than Monday, 17 July
NOTE: Interfaces will be point to point, no middleware solution would be utilised
Foundation Systems architecture minus Staffware
A subset of key order-related interfaces.
Foundation Systems-Lite and the ‘key’ interfaces will be on line for 30 September
  a ‘best efforts’ approach to other non-priority interfaces.
Knowledge
DB

## Slide 11: Option 2 – Well at least it is closer to what we want, where’s the trap
Meets more of the businesses needs for automated processes
Provides a better solution for large volumes of orders and queries
Ensures a higher level of data quality
  Reduced data entry errors
Reduces manual processes
Risk! This solution is at best a compromise, the provides the business with some automated integration and allows for a 30 September Launch, however the risk potential is significantly higher. The risk is not only that around delivery but also
Web presentation displays all your ‘dirty little secrets’ to the world
  Bugs will be immediately obvious to users of the system
Parallel development activity
  Building interfaces against a moving target
Still requires some manual support activities
The reduction in time for analysis and testing increases the risk of failure
Insufficient time for training
Interim solution could become ‘the solution’
Stability
  Bug-fixing should be expected
Potential delays the for the development of SMENION II
  Valuable resources could be distracted by operational and maintenance issues in production
Other related projects may not be ready to support automated interfaces
  Staffware
  Call Centre build
  Network
Point-to-Point interfaces will need to maintained and updated every time a core system is changed
  Recommend replacing the point to point interfaces after a more mature middleware solution is developed and tested
Benefits
Risks

## Slide 12: Administrative and Implementation Risks
Basics and administration
  Decision making process for final go live may delay project start
    Please Note: Deloitte Consulting is prepared to begin development activities with a signed statement of work
  Workspace and infrastructure
    Deloitte Consulting will provide a development environment and if necessary a testing environment in our Solution Centre in Bath
    However, workspace and minimal infrastructure will be necessary for the Design, Process and Training teams who will be based in Munich at Company Z
Structure
  No visibility of the related project plans, some of which hold key predecessors tasks for the SMENION I
Resources
  Availability of VIAG resources for Bath
  Holiday time. This implementation will be conducted over key holiday time for most of Europe. This may impact the availability of Company Z, Deloitte Consulting and key vendor partner resources
Project risks
  Staffware set-up, the network is responsible for their own instance of Staffware, however they have raised the issues of whether or not they will have the resource or the budget to develop on the SMENION I timeline
  Company Z Security policy for internet access through the Company Z firewall
    The current VI security policy will not allow any near-real-time integration of third-Parties through the firewall
  CTI is not purchased yet; CTI integration is in scope of SMENION I however
  Interdependencies from bill format solution project
  Middleware solution - IT-standard for interfacing (BEA-WebLogic) has never been implemented in a production environment, as currently specified it won’t work with Siebel and it is largely supported by external resources
The current process for IP Provisioning and Activation is highly manual and requires a technical knowledge. The process as described (meeting on 4 July 2000) could not be performed by your average Customer Service Representative, nor third-party dealer
Requirements for IP provisioning and Activation (to include the Mail Server) have not been documented
  It is highly unlikely that any functionality specific or unique to IP provisioning/activation will be included in the SMENION I system release (30/9)

## Slide 13: Proposed Team Structure
IT
Management
NW
Management
Business
Management
Operations
Management
Steering
Committee
Sponsor
W. Fraas
Programme
Management
C. Ortmaier
+ P. Ratzer (DC)
IT PM
C. Lorenz
NW PM
J. Koenel
Bus PM
[Open]
Ops PM
[Open]
Project Team
Revenue /
Mediation C. Swatonek
Interface B. Dhaens*
Tech.
Infrastructure
H. Tyler
Training /
Change
J. Wolter
Web, CRM & OM
R. Hickcox
Workflow Viag Resource
Solution
Architecture
J. Ramsey
Process
J. Wolter
Support Team
K. Pomschar
G. van Nispen
X. Laury
DC
Delivery
Management
R. Hunt Robinson
Team structure assumes a senior Steering committee who will be responsible for design sign-off, status review, issues resolution and escalation and co-ordinating and clearing action items to the different business functions at Company Z.

## Slide 14: Solution Project Plan – Option 1 (through October 13)
The project plan for option 1 only depicts the activities for the initial release. This was done to provide an apples to apples comparison with the Option 2 plan. It is important to note that the Option 1 plan is more in line with

## Slide 15: Solution Project Plan – Option 2 (through October 13)
The project plan mirrors that of the draft project plan delivered on 23 July. With 2 key changes: Requirement must be frozen on 10 July, Designs must be sign-off by the steering group by 21 July. Please note this plan only allows for 10 days of User Acceptance Testing

## Slide 16: Budgetary Costs Estimates (through 13 October 2000)
Costs represented are for estimation purposes only. Actual costs will vary based on negotiation and existing Company Z agreements.
† Assumes that in Option 1, Interface development for Rollout 2 will commence in month 2
* Assumes that in Option 2, All Staffware development will be performed by the Network Function
Option 1
Option 2
$2,355,000.00
$280,000.00
$750,000.00
$3,050,000.00
$3,050,000.00
$2,355,000.00
$280,000.00
$750,000.00
Total
($125,000.00)
($125,000.00)
$13,967,000.00
$14,432,000.00
Software Licences
Hardware Purchases
  Development Environment Fees
  Training/Testing Environments
  Production (3-tier architecture)
Implementation Fees
  Design & Solution Architecture
  Web, CRM & OM
  Workflow*
  Billing/Mediation
  System Integration †
  Technical Integration
Project Management & Quality Control
Process & Training Fees
Expenses
less Phase 0 credit

## Slide 17: Appendix A- Change Control Process

## Slide 18: Appendix B – Configuration Management

## Slide 19: Appendix D—Process & Requirements Analysis
Version 4.0
5 July 2000

## Slide 20: Appendix E—Gap Analysis SMENION
Version 1
5 July 2000

## Slide 21: Appendix F— Siebel Module List

## Slide 22: Module List – Part 1

## Slide 23: Module List – Part 2

## Slide 24: Appendix G – Feedback received on Process Analysis Document
Contact Feedback on incorporated?
  Wolfgang Breithaupt Customer Service partly (Funct. Matrix)
  Martin Kracker Process Analysis Functional Matrix see Wolfgang Breithaupt
  Claudia Lorenz Markus Klug Stefan Strobel Functional Matrix see Wolfgang Breithaupt
  Frank Gillmeyer Billing (Funct. Matrix) partly
  Johann Kuehnel Andreas Heine Service provisioning yes
  Graham Matty e-Business partly
The following is a list of the feedback we have received on the process analysis document and the action taken as a result.

## Slide 25: Appendix H—Gap Analysis Status
The following is a of gap areas identified in the Process Analysis document issued on 23 June and the current status of the gap area.