## Sheet1
Lessons Learned | Why | Implication | Phase
Conduct focused design workshops, led by the solution architecture team, for each core process. Invite subject matter representatives from each package team. | Each application and a middleware expert will be able to provide information on their part of their process, that no other participant may have. | Having everyone in a room together is the best way to drill down to enough detail to develop the high-level design. Build in flexibility as much as possible. Anticipate future requirements (client vision) | High-level design
Agree up front on having accessibility to key technical experts from package vendors. Leverage existing relationships with the vendors to ensure responsiveness. | Design workshops will generate detailed technical questions which can only be answered by the vendor. For example, table structures and element attributes are sometimes ill-documented but need to be synchronized across different packages. | Real-time responses are essential to avoiding bottlenecks and keeping the workshop moving forward. | High-level design
Agree up front on having accessibility to key technical experts from the client, in particular from engineering. | Operational and Business systems will require inputs from the network (eg, circuit Ids, call detail record formats) in order to link these to commercial information (eg, customer accounts, service requests) | Given the technical nature of the services, input from engineering will be key to providing the right type of linkage between commercial systems, operational systems, and network systems. This will help provide a consolidated view of a service. | High-level design
Workshop participants will need to communicate and evangelize the high-level design back to their teams (ie, each package representative, the representative from the integration team, and the technical infrastructure team). Likewise they will need to feed back any comments from their team back to the workshop. | Each team will need to understand the high-level design as it crystalizes in order to do their detailed focused design and craft coherent processes. Similarly, each team will generate questions and issues that can only be resolved at a high level. | Having the workshop representatives serve as bi-directional information conduits with their teams will ensure consistency with the high-level design as well as across each package / process area. | High-level design
Use the Systems Architecture Design documentation from prior projects as a baseline. | New members of the team will need a reference point to work towards in terms of level of detail, structure and content. | Using prior documentation as a guideline will prevent the team from wasting time and re-inventing the wheel, while ensuring coverage of all key areas and guaranteeing consistency. | High-level design
Develop a short list of best-of-breed packages for evaluation which are known to provide MOST of the desired functionality out of the box, based on prior experience. | There are many different vendors supplying solutions for each core process. However, a select few are considered to be best of breed. Furthermore, evaluating every single package would be extremely time-consuming. | Focusing on only the top two or three packages via an accelerated selection process will ensure a timely implementation. | Package Selection
During the selection process, map functionality to requirements only to ensure full coverage. Do NOT map BASIC package functionality. | Based on experience, the best-of-breed packages already cover standard functionality. Therefore, the differentiation amongst the top package is very likely to be the most leading-edge functionality required by the services. For example, most billing packages perform rating, but not all are massively scalable, while others vary greatly on performance. | Perform the package selection based mostly on availability of key functionality and other characteristics. | Package Selection
Select final packages in the context of the final solution, not independently. | There will be overlapping functionality among many of the packages (eg, some billing systems will perform some CRM and ERP functions as well) Take into account future requirements (ie products, indirect channels etc) | By taking a holistic architectural view, data ownership can be quickly assigned to each package. For example, the CRM system will likely manage the contacts list, where as the billing system would better manage pricing and the service catalog. Therefore, it is immaterial that the billing system not be able to manage the contact list, and vice-versa. | Package Selection
Cross-check technical storyboard against core processes. | If core processes are developed independently of the technical high-level design, there is a substantial risk that the two will not align, meaning that the system design will not support the core processes. | This will ensure integrity and consistency at every level - package design, process design, interface design, and data architecture. | High-level Design
Develop an enterprise-wide data architecture (eg, in the form of an entity relationship diagram) | There will be overlapping functionality among many of the packages (eg, some billing systems will perform some CRM and ERP functions as well). There is a danger of ambiguity around which system is performing what function unless this is defined early on. | This global view will identify which package owns which data (eg, CRM system owns the customer contact list, not the billing system), will identify table keys, and synchronize tables across different packages) | High-level Design
Cross-check interface specification against data architecture. | The data flows will start on specific package tables and end on others. There is a risk of data syntax and structure inconsistencies if the middleware is unaligned with individual package data architectures, and implicitly with the enterprise-wide data architecture. | The integration team will need to work collaboratively with the solution architecture team to ensure full reconciliation. | High-level Design
Leverage requirements documentation from previous similar projects as a baseline. | There is a risk of wasting time by re-generating standard requirements from scratch. | By obtaining a list of standard requirements from prior documentation, the team can focus on KEY functionality that will differentiate the service offering. | Requirements
Limit input to requirements to key management staff. Ensure that a product manager is assigned ownership of requirements related to their particular service. | There is a risk that too many inputs to the requirements process will lead to a lack of focus (the "too many cooks spoil the broth" effect). | The product manager is ultimately responsible and is incented by the success of their product in the marketplace. Therefore, they should have total ownership of their related set of requirements and should have the authority and upper level support for driving this process. | Requirements
Adopt a combined "top-down" and "bottom-up" approach to developing requirements. | There is a significant risk that lofty product goals and the associated business requirements will not be supported by the technology. | By first following a top-down requirements development approach, a target set of functional requirements can be developed. These can then be mapped against package functionality to develop a "delta" list. Part of the delta will be requirements that cannot be met by the package functionality, in which case the business requirements should be updated accordingly. The remainder of the delta list will consist of functionality which could engender valuable business capabilities. Likewise, functionality that is not useful can be ignored. | Requirements, Package Selection
Ensure consensus of service definitions and related business requirements up front in the process by ALL key stakeholders. | There will likely be wide disagreement on service characteristics among different parts of the organization. For example, marketing will tend to enrich its definitions with both technical performance and functionality, while engineering will have a better view on what their network infrastructure will actually allow. Similarly, the operations group will likely request less ambitious service level targets based on their own constraints. | Mandating a consensus early on will avoid a situation of rapidly changing requirements as well as confusion and miscommunication. | Requirements
Obtain a commitment from upper management to meet daily with the solution architecture team to review and resolve issues. Define "service levels" outlining required level of responsiveness. | Given the extremely fast pace of the project, management staff will be pulled in different directions by multiple time demands, limiting their ability to focus on the most pressing goal - that of product launch. | Defining service levels will promote issue transparency and resolution. | All
Leverage the greenfield environment to define a focused transitional org. structure which is optimized for product implementation. | Given that the organization will experience a substantial growth and transition phase, it will need to be organized effectively to focus on its strategic goal of launching the first services to the marketplace. | Forming a focused structure organized around the process of new-product implementation, working collaboratively with the systems integrator to achieve this goal, will optimize the implementation by aligning strategic goals with personal goals. | Next Phase Workplan
Leverage Deloitte Consulting global talent pool and knowledge repository to avoid re-inventing the wheel. | There is a risk of a newly-formed team being unaware of key tools available to them, thus limiting them to not being fully efficient. | Deloitte Consulting has deep expertise distributed throughout its global practice who could bring a high degree of insight into solving issues quickly and effectively. Team leads will be aware of state-of-the-art thoughtware and deliverables and leverage these accordingly. | High-level Design
Adopt a prototyping philosophy so that key functional specifications can be tried quickly. | A prototyping approach will allow the design team to converge on an solution more quickly than a traditional waterfall approach. | During high level design, key package functionality should be prototyped in the test environment in order to verify that it works. If there are issues, these can be fed back to the design process in real time for resolution. | High-level Design